Topic: NASA-LSP-2026-014: In-Situ Resource Utilization for Lunar Surface Construction

Contract: NNX25-LR-0042 (Phase I) → Phase II Proposal

Title: Lunar Regolith Sintering for In-Situ Habitat Printing

Phase: SBIR/STTR Phase II — 12 months, $1,500,000 total

Principal Investigator: Principal Investigator (Example Institute of Selenology)

Co-Investigator: Co-Investigator (Example Institute of Selenology)

Submission Date: 2026-04-15

Proposal Type: Direct-to-Phase-II

# 1.0 Introduction

The cost of launching mass to the lunar surface is the dominant constraint on every long-duration mission profile. Conventional habitat designs treat structural materials as cargo and budget every kilogram against transit fuel; under that model, surface infrastructure scales linearly with launch tonnage and a single permanent outpost remains an order of magnitude beyond program affordability.

This proposal generalizes our Phase I prototype into an operational in-situ resource utilization (ISRU) platform that prints load-bearing structures directly from lunar regolith. The Phase I effort (Aug 2025–Feb 2026, $250,000) sintered JSC-1A regolith simulant into compression-test coupons reaching 27.4 MPa — comparable to a low-grade masonry block — at a print resolution of 220 µm [1]. Phase I demonstrated that the sinter profile, gantry kinematics, and dust-tolerant powder bed all work as an integrated system on Earth.

Phase II (12 months, $1,500,000 total) carries the prototype from terrestrial vacuum-chamber operation to a flight-qualifiable subsystem rated for the lunar thermal and radiation environment. See Section 4.0 for the full milestone schedule.

# 2.0 Specific Aims

## 2.1 Aim 1 — Vacuum-Compatible Sinter Profile

Develop and characterize a sinter profile that produces structurally sound parts under lunar surface conditions (10-9 Torr, diurnal cycling between -173 °C and 117 °C). Phase I validated the profile at 1 atm in a glovebox; Phase II re-runs the parameter sweep in a thermal-vacuum chamber and quantifies the gap.

Hypothesis: a stepped 1380 °C → 1420 °C profile compensates for reduced convective heat loss in vacuum and yields ≥25 MPa compressive strength on JSC-1A coupons.

## 2.2 Aim 2 — Dust-Mitigation Recoater

Replace the Phase I roller recoater with a dust-tolerant blade mechanism qualified for the abrasive fines characteristic of mature lunar regolith. Failure mode analysis of Phase I prototypes showed recoater binding as the leading defect source; this aim eliminates that failure mode.

## 2.3 Aim 3 — Closed-Loop Quality Control

Integrate inline thermal-imaging-based defect detection into the print path, with a per-layer go/no-go decision that pauses printing on anomaly. Targets ≥95% defect-detection sensitivity at <2% false positive rate, validated against ground-truth metallography.

# 3.0 Technical Approach

## 3.1 System Architecture

The Phase II prototype is a five-subsystem integrated printer. Figure 1 shows the layout; descriptions of each subsystem follow.

Figure 1: System architecture for the Phase II lunar regolith printer. Five interlocking subsystems — feedstock handling, gantry, sintering, dust mitigation, and quality control — deliver an autonomous print loop.

Feedstock handling. A vibratory hopper meters JSC-1A simulant into a heated buffer that drives off adsorbed water before the powder reaches the print bed. Lunar-relevant grain size distributions (median 70 µm, with 10% sub-20 µm fines) drive the hopper geometry.

Gantry kinematics. A three-axis CoreXY gantry positions the sinter head over the 220 µm-resolution print bed. The gantry is rated for thermal-vacuum operation and uses graphite bushings rather than oil-lubricated bearings to survive the sub-Torr environment.

Sintering. A 250 W diode laser delivers the focused thermal input to the powder bed. The Phase I stepped profile is documented in Aim 1; we extend that profile in Aim 2 for the vacuum-chamber gap.

Dust mitigation. The recoater is a blade-edge design with a purge-gas knife (low-flow, recycled) that re-fluidizes settled fines. This subsystem is the focus of Aim 2.

Quality control. An inline 8 µm thermal camera images each layer post-sinter; layer-level features feed a small CNN classifier trained against metallography ground truth. Aim 3 develops this classifier.

## 3.2 Scientific Foundations

The approach builds on three demonstrated foundations:

- Solid-state sintering kinetics for binary basaltic glass

systems are well-characterized in the powder-metallurgy literature [2]. Our Phase I profile leverages the iron-rich phase of JSC-1A as a sintering aid.

- Vacuum-compatible drive trains at the scale of a desktop

gantry have flight heritage from cubesat reaction wheel assemblies.

- Inline thermal-imaging defect detection is a mature technique

in industrial metal AM [3]; we adapt the published feature pipeline rather than inventing a new one.

## 3.3 Key Technical Risks

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Coupon strength <25 MPa in vacuum | Medium | High | Stepped profile (Aim 1); fall-back binder-jet path |
| Recoater binding on fines | High | Medium | Blade redesign + purge knife (Aim 2) |
| QC false-positive rate too high | Low | Low | Larger training set, ensemble classifier |

A more detailed five-row register lives in tables/risk_register.tsv and is rendered below in Section 4.2.

# 4.0 Project Plan

## 4.1 Milestone Schedule

Phase II is organized as six bimonthly milestones over 12 months. Each milestone includes a deliverable, a quantitative success criterion, and a go/no-go review. The full schedule lives in tables/milestones.csv so any timeline edit happens in one place and propagates to PDF, HTML, and Word builds:

| Milestone | Months | Deliverable | Success Criterion |
| --- | --- | --- | --- |
| M1: Vacuum profile sweep | 1-2 | Sinter parameter map (vacuum) | Coupons at >=25 MPa in vacuum |
| M2: Recoater redesign | 3-4 | Blade + purge-knife prototype | <2% recoater bind rate over 50 layers |
| M3: QC pipeline | 5-6 | Inline classifier + training set | >=95% sensitivity / <2% FP rate |
| M4: Integrated print campaign | 7-8 | Five 200x200x100 mm test articles | All five pass dimensional + strength QC |
| M5: Environmental stress testing | 9-10 | Diurnal cycle survival | Test articles pass 30 thermal cycles |
| M6: Final demonstration | 11-12 | Flight-qualifiable subsystem package | TRL 6 review with NASA stakeholders |

## 4.2 Risk Register

The five-row engineering risk register, expanded from Section 3.3, is loaded from a TSV so individual rows can be edited without touching markdown:

| Risk | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| Coupon strength below 25 MPa in vacuum | Medium | High | Stepped profile (Aim 1); binder-jet fallback path | PI |
| Recoater binding on lunar fines | High | Medium | Blade redesign + purge knife (Aim 2) | Co-I |
| QC false-positive rate exceeds 2% | Low | Low | Larger training set, ensemble classifier | Consultant |
| Gantry bushing failure under cycling | Medium | Medium | Graphite bushings; quarterly inspection | Co-I |
| Schedule slip on M3 integration | Medium | Medium | M3 has float; M4 demonstration scope flexible | PI |

## 4.3 Team

The PI (materials engineering, additive manufacturing) and Co-Investigator (vacuum-compatible drive train design) each contribute 20% effort across the 12 months. A graduate student (40% effort) executes the bench experiments under PI supervision. A consulting expert in inline thermal-imaging QC supports Aim 3 at 40 hours over the full period.

## 4.4 Facilities

All work runs in the Example Institute of Selenology vacuum-chamber facility (10-9 Torr base pressure, 1 m × 1 m working volume), with metallography and mechanical-test infrastructure co-located. No subcontracted facilities are required.

# 5.0 Broader Impact

## 5.1 Mission Relevance

A Phase II-qualified ISRU printer reduces the launch mass of the first permanent lunar habitat by ≥40% by replacing structural cargo with regolith-printed elements. The same technology generalizes directly to Mars surface operations using basaltic regolith analogues — the printer hardware is identical; only the sinter profile changes.

## 5.2 Commercialization Pathway

Beyond the immediate NASA mission application, the Phase II prototype provides the technology base for two commercial trajectories:

- Terrestrial vacuum AM: industrial customers in semiconductor

packaging and aerospace turbine components increasingly demand vacuum-compatible printers; our gantry IP transfers directly.

- Lunar economy services: as launch cadence increases, on-surface

construction-as-a-service becomes a real market. The printer is the enabling capability.

## 5.3 Knowledge Transfer

All sintering profiles, gantry CAD, and QC training data developed under Phase II are released as a permissively-licensed reference design at the program's conclusion, with the explicit goal of seeding a domestic ISRU supply chain.

# References

[1] Principal Investigator, Co-Investigator. Phase I Final Report: Lunar Regolith Sintering Feasibility. (2026).

[2] Jiwon Park, Rania Hassan, Luis Vasquez. Solid-State Sintering Kinetics of Iron-Bearing Basaltic Regolith Simulants. Journal of Lunar Materials Engineering 18(3), 214–231 (2024). https://doi.org/10.1234/jlme.2024.0218

[3] Adaeze Okonkwo, Per Lindqvist. Inline Thermal-Imaging Defect Detection in Powder-Bed Metal Additive Manufacturing: A Practitioner Survey. Proceedings of the International Conference on Additive Manufacturing, 88–104 (2023). https://doi.org/10.5678/icam.2023.011